## Sem2 Timeline
Semester 2 Project Timeline | [15 empty] | Planned / In progress | Thursday 4pm supervisor meeting Wednesday 4pm group meeting
Specific Tasks | Who | Deadline | 2020-08-07 | 2020-08-14 | 2020-08-21 | 2020-08-28 | 2020-09-04 | 2020-09-11 | 2020-09-18 | 2020-09-25 | 2020-10-02 | 2020-10-09 | 2020-10-16 | 2020-10-23 | 2020-10-30 | Done / Exhausted
Task 1: Aquire Research Data, initial data exploration |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Mid-Sem Break | Week 10 | Week 11 | Week 12 | URGENT | DOCUMENT ALL PROCESSES
Aquire client data & Initial Meeting | ALL | Week 2
Initial data exploration | ALL | Week 2
Catch up with Kate / distribute tasks | ALL | Week 2
Join data | Raelene | Week 3
Data Summary | Xin | Week 3
Random forest, decision tree, SVM | Xinhui | Week 4
Logistic regression | Ziyan | Week 4
Platform exploration | Bing | Week 4
Catch up with Client | ALL | bar: Week 3 to Week 4
Aquire donor data from client | Bing | Week 4
Task 2: Preprocessing, fitting Lead Models
Build ER diagram, database | Bing | Week 5
Data preprocessing, add new features | Xin | week 5
Task tracking, build Neural Network | Raelene | Week 5 | bar: Week 1 to Week 2; Week 6 to Week 9
Logistic Regresison | Ziyan | Week 5
Random forest, decision tree, SVM | Xinhui | Week 5
Evaluation and Analysis | ALL | Week 6 | bar: Week 5
Task 3: Parameter tuning, compare methods, visualisation
Check all the code and results on github | Bing | Week 7 | bar: Week 3 to Week 5
Graph exploration, create dashboard | Xin | Week 7 | bar: Week 1 to Week 6; Week 8 to Week 9
Update Neural Network, create report outline | Raelene | Week 7 | bar: Week 3 to Week 5
Update Random forest, decision tree, SVM, rank features | Xinhui | Week 7 | bar: Week 3 to Week 5
Logistic Regresison, rank features | Ziyan | Week 7 | bar: Week 3 to Week 5
Task 3: Inference
Analysis on hypothesis | ALL | Week 8 | bar: Week 8 to Week 9
Impact on CRM's Strategy | ALL | Week 8 | bar: Week 8 to Week 9
Further exploration of hypothesis | ALL | Week 8 | bar: Week 8 to Week 9
Presenting findings to clients | ALL | Week 9 | bar: Week 8 to Week 9
Task 4: Fianl Presentation / Submission / Deployment
Deploy model for client | ALL | Week 10
Report Draft | ALL | Week 9 | bar: Week 8 to Week 9
Report Finalised | ALL | Week 10
Presentation | ALL | Week 11

## Weekly Tasks
Week | Who | Tasks | Deadline
Week 3 |  | Joint leads/accounts
| Raelene | identify leads without account | Sat
| Xin Li | doucment characteristics of missing columns
summarize the data
| Xinhui | feed the entire table in the models | Fri
Ziyan
| Bing | Platform exploration | Fri
Week 4 |  | Agree on how to handle missing values
which ones to omit
which ones to imputate
how to imputate
document all processes

## Sem1 Timeline
Project Timeline
Semester 1
Specific Tasks | Who | Start | End |  |  |  | Completed |  | To be done
Task 1: Project definition and Outline |  |  |  | Week 1 | Week 3 | Week 5 | Week 7 | Week 9 | Week 11 | Week 12
Background knowledge | ALL | Week 4 | Week 6
Finalising Problem Domain | Bing | Week 6 | Week 7
Literature review daft | ALL | Week 4 | Week 7
Task 2: Public Data: Pre-processing and analysis
Public Dataset Gathering | Raelene | Week 8 | Week 11
Data Cleaning | Xinhui | Week 8 | Week 11
Data initial Analysis | Xin | Week 8 | Week 11
Build analysis Method | Ziyan | Week 9 | Week 11
Result and Analysis | Bing | Week 9 | Week 11
Draft report | ALL | Week 10 | Week 11
Timeline | Xin | Week 11 | Week 12
Finalise report | Raelene | Week 12 | Week 12
Privacy Impact Assessment | Bing | Week 12 | Winter Sem
Semester 2
Specific Tasks | Who | Start | End
Task 1: Client Data: Pre-processing |  |  |  | Week 1 | Week 3 | Week 5 | Week 7 | Week 9 | Week 11 | Week 12
Initial data exploration | ALL | Week 1 | Week 2
Preprocess the data | Xin Li | Week 1 | Week 2
Fiting missing values | Xinhui | Week 1 | Week 2
Task 2: Fitting Lead Models, parameter tuning
Logistic Regresison | Bing | Week 3 | Week 4
Random Forest | Ziyan | Week 3 | Week 4
Neural Network | Raelene | Week 3 | Week 4
Evaluation and Analysis | ALL | Week 5 | Week 6
Task 3: Inference
Analysis on hypothesis | ALL | Week 7 | Week 8
Impact on CRM's Strategy | ALL | Week 7 | Week 8
Further exploration of hypothesis | ALL | Week 7 | Week 8
Presenting findings to clients | ALL | Week 8 | Week 9
Task 4: Fianl Submission
Report Draft | ALL | Week 8 | Week 9
Report Finalised | ALL | Week 9 | Week 10
Presentation | ALL | Week 10 | Week 12